DIGITAL LENDING — PORTFOLIO OPTIMIZATION

End-to-End Engagement Execution Roadmap

A two-week consulting delivery plan to a final submission deadline of June 10

Prepared by:  Engagement Management Office (EM · Senior Risk Consultant · Data Science Lead · PMO)

Prepared for:  Project sponsor & evaluation panel (senior partners, fintech executives, risk leadership)

Engagement window:  Day 1 (June 1) through Final Submission (June 10) — 10 calendar days

Governing standard:  Lead with strategic recommendations substantiated by data — never data outputs in search of a conclusion.

Final deliverables:  (1) Credit Policy Recommendation Report (4–6 pp., addressed to the CRO)  ·  (2) Stakeholder Presentation Deck

CONFIDENTIAL — INTERNAL ENGAGEMENT PLANNING DOCUMENT

# Contents

1.  Executive Project Strategy	3

2.  Workstream Breakdown (A–K)	5

3.  Dependency Map	13

4.  Day-by-Day Timeline Until June 10	14

5.  Risk Register	17

6.  Quality Gates	18

7.  Backtesting & Validation Plan	21

8.  Final Submission Checklist	22

# 1. Executive Project Strategy

## 1.1 Engagement thesis

This engagement converts a digital lender's raw customer, loan, repayment and behavioural data into a recommendation-led credit policy that strengthens risk assessment, detects delinquency early, and optimises pricing and product strategy for sustainable, risk-adjusted growth. We are not building a data science demo; we are building a decision the Chief Risk Officer can sign. Every analytical artefact must trace forward to a policy lever and backward to a number the panel can defend.

Because participants design their own synthetic dataset, the engagement carries an unusual risk: the analysis is only as credible as the data is realistic. We therefore front-load data architecture and a hard data-realism gate, then protect a dedicated validation window before submission so the team never trades rigour for a deadline.

## 1.2 Operating model and ownership

Four notional roles run the engagement. On a small team one person may wear several hats, but the accountabilities below must each have a named owner.

| Role | Primary accountability | Owns workstreams |
| --- | --- | --- |
| Engagement Manager (EM) | Storyline, client logic, recommendation quality, panel readiness, final sign-off | A, I, J, K |
| Senior Risk Consultant | Credit-risk realism, segmentation logic, early-warning design, policy feasibility | A, E, F, G |
| Data Science Lead | Synthetic data generation, EDA, modelling, backtesting, reproducibility | B, C, D, E, F |
| PMO / QA | Timeline, dependencies, quality gates, risk register, submission checklist | All (governance) |

## 1.3 Guiding principles

- Recommendation-first. Each workstream states the decision it informs before any chart is drawn.

- Realism over volume. A small, behaviourally coherent dataset beats a large, statistically implausible one. Relationships in the brief's data table are treated as design constraints, not suggestions.

- Simple, defensible methods. Prefer transparent, interpretable techniques a risk committee will trust over black-box accuracy that cannot be governed.

- One number, one source. Every headline figure (default rate, uplift, CAC payback) has a single owning calculation in a controlled workbook; the report, deck and dashboard read from the same source.

- Gate before you build. No workstream begins until its upstream quality gate has passed. Rework late in a 10-day sprint is fatal.

## 1.4 Key questions mapped to the answer

The brief's five questions are the spine of the storyline. Each maps to an owning workstream and a final-deliverable home.

| # | Key question (abridged) | Answered by | Lands in |
| --- | --- | --- | --- |
| Q1 | Which customer segments differ materially in risk/repayment, and what defines them? | E — Segmentation | Report §2; Deck slides 6–7 |
| Q2 | How do acquisition channels & onboarding affect quality, CLV and unit economics? | D — Channel & unit economics | Report §2; Deck slide 8 |
| Q3 | Which products, ticket sizes and tenures best balance growth vs. risk? | D, G — Product economics | Report §4; Deck slide 9 |
| Q4 | How should pricing/approval/tenure be tailored across segments? | G, I — Optimisation & policy | Report §4; Deck slides 11–12 |
| Q5 | What should leadership monitor to manage risk and growth proactively? | H — Dashboards | Report §5; Deck slide 13 |

## 1.5 Critical path and cadence

The critical path runs Data design → Data generation → EDA → Segmentation → Early-warning model → Optimisation → Recommendation → Report/Deck → QA → Submit. Dashboards (H) run in parallel from the EDA outputs and are not on the critical path. Any slip on the critical path consumes buffer directly, so those tasks get first call on people and review attention.

- Daily cadence: 15-minute morning stand-up (yesterday / today / blockers) and a 20-minute end-of-day checkpoint against the day's expected outputs.

- Gate cadence: Seven mandatory quality gates (§6). A gate is binary — pass or fix-then-pass — and is logged by PMO before the next workstream starts.

- Buffer policy: The plan is engineered to reach “submission-ready” by end of Day 9 (June 9). June 10 is a protected buffer and final-review day, not a working day for new content.

# 2. Workstream Breakdown

Eleven workstreams (A–K) carry the engagement. Each is framed by the decision it informs, the work it does, what it produces, who owns it, and what it depends on. Variable-level and slide-level detail is included where the brief demands it.

## Workstream A — Problem Framing

Owner: Engagement Manager + Senior Risk Consultant    Decision it informs: What “good” looks like for the CRO and how success will be measured.

- Business objective. Strengthen credit-risk assessment, enable early delinquency detection, and optimise pricing/product to grow the book on a risk-adjusted basis — stated as one sentence the CRO would repeat.

- CRO expectations. Forward-looking, decision-ready insight; defensible numbers; policies that are operationally feasible inside current systems; a monitoring view leadership can run weekly.

- Success metrics. Reduction in expected 90+ DPD / credit loss rate; improvement in risk-adjusted return (RAROC / NIM-after-loss); CAC payback and CLV by segment; share of losses pre-empted by early-warning flags (lead time in days).

- Final recommendation requirements. One headline policy plus 2–3 supporting levers, each with quantified impact, implementation owner, and a guardrail metric.

Deliverable: one-page engagement charter (objective, scope, metrics, definitions of default/delinquency, out-of-scope items).

Depends on: nothing (start).  Feeds: B, I, J, K.

## Workstream B — Synthetic Data Design

Owner: Data Science Lead + Senior Risk Consultant    Decision it informs: The schema and variable relationships that make all downstream analysis credible.

A four-table architecture mirrors the customer journey and keeps grain explicit. Relationships are designed to honour the brief's expected directions (weaker profiles → higher risk; deteriorating payment behaviour precedes default; higher volatility → higher delinquency; faster/cheaper acquisition may carry higher risk).

### B.1 Dataset architecture (tables and grain)

| Table | Grain (one row =) | Approx. rows | Joins on |
| --- | --- | --- | --- |
| customers | one customer | ~40,000 | customer_id |
| loans | one loan (origination) | ~50,000 | customer_id → loan_id |
| repayments | one loan × one scheduled period (panel) | ~550,000 | loan_id, period |
| behaviour_monthly | one customer × month (alt-data panel) | ~480,000 | customer_id, month |

### B.2 Variable dictionary — must-have vs. nice-to-have

M = must-have (analysis breaks without it); N = nice-to-have (adds realism/depth). The last column maps each variable to the key question(s) it serves.

Customer attributes

| Variable | M/N | Definition / values | Serves |
| --- | --- | --- | --- |
| customer_id | M | Unique key | all |
| region_type | M | Urban / semi-urban / rural | Q1 |
| income_proxy_band | M | Low / mid / high (derived from declared + inferred) | Q1 |
| employment_type | M | Salaried / self-employed / gig / informal | Q1 |
| credit_quality_indicator | M | Bureau band A–E + thin-file flag | Q1, Q4 |
| first_time_borrower | M | Y/N | Q1, Q2 |
| age | N | Years (18–65) | Q1 |
| relationship_tenure_mo | N | Months since first loan | Q1, Q3 |

Loan & product attributes

| Variable | M/N | Definition / values | Serves |
| --- | --- | --- | --- |
| loan_id | M | Unique key | all |
| product_type | M | Personal / SME working capital / BNPL | Q3 |
| ticket_size | M | Loan amount (product-specific ranges) | Q3, Q4 |
| tenure_mo | M | Contractual months | Q3, Q4 |
| interest_rate_apr | M | Priced APR | Q3, Q4 |
| origination_risk_grade | M | A–E at underwriting | Q1, Q4 |
| origination_date | M | Cohort anchor | Q2 |
| approval_decision | N | Approved / declined (for approval analysis) | Q4 |

Repayment attributes

| Variable | M/N | Definition / values | Serves |
| --- | --- | --- | --- |
| dpd | M | Days past due at each period | Q1, Q5 |
| delinquency_bucket | M | Current / 1–30 / 31–60 / 61–90 / 90+ | Q1, Q5 |
| paid_on_time_flag | M | Per scheduled installment | Q1 |
| partial_payment_flag | M | Paid < EMI in period | Q1 |
| missed_payments_cum | M | Cumulative misses to date | Q1 |
| prepayment_flag | N | Early full settlement | Q3 |
| roll_rate | N | Bucket-to-bucket migration | Q5 |

Behavioural signals

| Variable | M/N | Definition / values | Serves |
| --- | --- | --- | --- |
| cashflow_consistency | M | Score 0–1; inflow regularity | Q1, EWS |
| balance_volatility | M | Std-dev of monthly balance proxy | EWS |
| spending_shock_flag | M | Sudden outflow spike in month | EWS |
| nach_bounce_count | M | Auto-debit failures (rolling 3m) | EWS |
| bureau_inquiry_velocity | N | New inquiries last 90d | EWS |
| app_engagement | N | Login / session frequency | EWS |
| credit_utilisation | N | For BNPL/revolving lines | EWS |

Acquisition, time & outcome attributes

| Variable | M/N | Definition / values | Serves |
| --- | --- | --- | --- |
| acquisition_channel | M | Digital ads / partner-embedded / referral / DSA / organic | Q2 |
| cac | M | Cost of acquisition (channel-driven) | Q2 |
| approval_tat_hrs | M | Onboarding turnaround time | Q2 |
| origination_cohort | M | Origination month (vintage) | Q2, Q5 |
| months_on_book | M | MOB at observation | Q5 |
| loan_status | M | Active / closed / written-off | Q3 |
| default_flag | M | Ever 90+ DPD | Q1, Q3, Q4 |
| value_proxy | M | Lifetime risk-adjusted margin (NPV proxy) | Q2, Q3 |

## Workstream C — Data Generation

Owner: Data Science Lead    Decision it informs: A reproducible, behaviourally coherent dataset that survives a realism challenge.

- Generation approach. Parameterised, seeded generator. Customer profile drives a latent risk score; risk score drives grade, pricing, behavioural signals and default hazard, so correlations are causal-by-construction rather than bolted on afterwards.

- Data-quality checks. No nulls in must-have fields; keys unique and joinable; values inside allowed ranges; panel completeness (every active loan has a row per period until closure/charge-off).

- Realism checks. Marginal distributions plausible (no negative tenures, sane APR ranges); delinquency rises with worse grade; roll rates monotonic; BNPL higher-frequency/lower-severity than SME; vintage curves age sensibly.

- Distribution validation. Compare generated marginals and key cross-tabs against the design targets below; flag any relationship that contradicts the brief's expected direction.

### C.1 Volumes, segment proportions and risk assumptions (design targets)

| Dimension | Design target (to validate, not to hard-code as truth) |
| --- | --- |
| Loans / customers | ~50,000 loans across ~40,000 customers; ~15–20% repeat borrowers |
| Observation window | 18–24 months of monthly snapshots; mix of seasoned and recent vintages |
| Product mix | Personal 45% · BNPL 35% · SME working capital 20% |
| Channel mix | Digital ads 35% · partner-embedded 25% · referral 15% · DSA 15% · organic 10% |
| Origination grade mix | A 15% · B 30% · C 30% · D 18% · E 7% |
| Blended 90+ default | ~6–9% lifetime; BNPL higher frequency / lower severity; SME lower frequency / higher severity |
| Risk gradient | Weaker profile, higher volatility, faster/cheaper channel → higher default — directionally, with noise |

Deliverable: seeded generator script + four CSV/Parquet tables + a one-page data dictionary and assumptions log.

## Workstream D — Exploratory Analysis

Owner: Data Science Lead + Senior Risk Consultant    Decision it informs: The current-state diagnosis the recommendations must improve on.

- Portfolio diagnostics. Book size, outstanding, weighted-average APR/tenure/ticket; overall delinquency and 90+ rates; concentration by product/grade/region.

- Cohort / vintage analysis. Default and delinquency by origination month and MOB; are newer cohorts deteriorating faster?

- Delinquency analysis. DPD distribution, bucket migration / roll rates, time-to-first-delinquency, recovery patterns.

- Channel performance. Default, CLV proxy, CAC and approval TAT by channel — directly answering Q2.

- Unit economics. Per-segment revenue (interest/fees) − expected loss − CAC − servicing = risk-adjusted contribution; CAC payback months.

Deliverable: EDA notebook + a curated chart pack (10–15 exhibits) that pre-stages the deck's diagnostic slides.

## Workstream E — Segmentation

Owner: Senior Risk Consultant + Data Science Lead    Decision it informs: The risk/value segments that anchor differentiated policy (Q1).

- Risk segmentation. Group loans/customers by default propensity and severity — candidate methods: rule-based grade bands, decision-tree segments, and k-means/k-prototypes on behavioural + profile features.

- Customer (value) segmentation. Risk × value matrix (e.g., high-value/low-risk “grow”, high-risk/low-value “exit/contain”).

- Product segmentation. Product × ticket × tenure cells scored on growth vs. risk (Q3).

- Methods to test. Heuristic/business-rule, tree-based, and unsupervised clustering — compared head-to-head.

- Selection criteria. Segments must be (i) materially separated on risk/value, (ii) interpretable to a risk committee, (iii) actionable via a policy lever, (iv) stable across cohorts and resampling.

- Validation approach. Silhouette / separation statistics, segment-size stability on bootstrap samples, and a “name the segment in one line” business test.

Deliverable: 4–6 named segments with profiles, sizes, risk/value metrics, and the policy hook for each.

## Workstream F — Early Warning System (EWS)

Owner: Data Science Lead + Senior Risk Consultant    Decision it informs: A flag that gives collections/credit lead time before 90+ default (Q5 enabler).

- Feature engineering. Trends and deltas, not just levels: rolling 3-month change in cashflow consistency, balance-volatility spikes, NACH-bounce streaks, partial-payment runs, utilisation creep, inquiry velocity.

- Behavioural triggers. Discrete rules (e.g., two consecutive partial payments + bounce in same month) layered with a model score for coverage.

- Prediction logic. Target = transition to 90+ DPD within a forward window (e.g., next 60–90 days). Prefer logistic regression / scorecard or gradient-boosted trees with monotonic constraints for governability.

- Candidate indicators. Falling cashflow consistency, rising balance volatility, first NACH bounce, partial-payment onset, spending-shock flag, rising utilisation, accelerating inquiry velocity.

- Validation framework. Out-of-time test, AUC/KS, precision/recall at chosen threshold, lift in top deciles, and — the metric that matters — average lead time (days) before default.

- Alert threshold design. Tie thresholds to collections capacity and the cost of a false positive vs. a missed default; propose green/amber/red bands with recommended actions per band.

Deliverable: EWS scorecard + trigger rules + threshold table with expected flag volume, precision and lead time.

## Workstream G — Portfolio Optimization

Owner: Senior Risk Consultant + EM    Decision it informs: Which levers, pulled how far, improve risk-adjusted outcomes (Q3, Q4).

- Pricing optimisation. Re-price by segment so APR covers expected loss + cost of funds + target margin; test risk-based pricing vs. flat pricing.

- Tenure optimisation. Identify tenures where default rises disproportionately; cap or restructure long-tenure exposure in weak segments.

- Approval optimisation. Move the approval cut-off using grade + behavioural score; quantify volume given up vs. losses avoided.

- Product strategy. Reallocate growth toward high-value/low-risk product–ticket cells; contain loss-making cells.

- Scenario testing. Baseline vs. 2–3 policy scenarios; project default, volume, revenue and risk-adjusted contribution for each.

- Sensitivity & trade-off analysis. Vary key assumptions (loss given default, channel mix shift, macro stress ±2–3pp default); show the growth-vs-risk trade-off explicitly so the CRO sees what each policy costs in volume.

Deliverable: scenario comparison table + tornado/sensitivity chart + recommended policy set with guardrails.

## Workstream H — Executive Dashboard

Owner: Data Science Lead + PMO    Decision it informs: What leadership monitors weekly to manage risk and growth (Q5).

Four linked views, each with KPIs, the visuals that carry them, and the decision they enable. Built from the same controlled source as the report.

| Dashboard | Key KPIs | Core visuals | Decision it enables |
| --- | --- | --- | --- |
| CRO summary | 90+ rate, risk-adj. return, new-business risk mix, EWS flags open | Single-screen scorecard + trend sparklines + RAG status | Is the book within risk appetite this week? |
| Portfolio monitoring | Outstanding, delinquency by bucket, roll rates, vintage curves | Stacked bucket bars, vintage line chart, concentration heatmap | Where is deterioration emerging? |
| Risk dashboard | Default by segment/grade/channel, EWS precision & lead time | Segment risk matrix, EWS funnel, threshold table | Which segments/flags need action now? |
| Growth dashboard | Volume & approval by channel, CAC, CAC payback, CLV | Channel bars, unit-economics waterfall, CLV vs. CAC scatter | Where to invest acquisition spend? |

Deliverable: dashboard mock-ups (static, presentation-grade) + KPI definitions; live tool optional and off the critical path.

## Workstream I — Recommendation Development

Owner: Engagement Manager + Senior Risk Consultant    Decision it informs: Turning findings into a prioritised, costed policy the CRO can approve.

- Finding → policy conversion. Each material finding is restated as a specific action (who changes what, in which segment, by how much), with a guardrail metric.

- Prioritisation. Score candidate policies on impact × feasibility × speed-to-implement; pick one headline + 2–3 supporting moves.

- Impact estimation. Quantify each policy: Δ default rate, Δ volume, Δ revenue, net Δ risk-adjusted contribution — with the assumption set and a plausible range, not a single hero number.

Deliverable: prioritised recommendation set with an impact table and an implementation note per policy.

## Workstream J — Report Development

Owner: Engagement Manager    Decision it informs: The 4–6 page Credit Policy Recommendation Report to the CRO.

Page allocation engineered to land inside the 4–6 page limit while covering every required element.

| Section | Content | Pages |
| --- | --- | --- |
| Executive summary | The ask, the headline recommendation, the projected impact — readable in 60 seconds | 0.75–1.0 |
| Risk segmentation findings | Named segments, what defines them, risk/value differences (Q1) | 1.0–1.25 |
| Early-warning signal logic | Indicators, trigger logic, thresholds, expected lead time (Q5) | 0.75–1.0 |
| Policy recommendation | Headline + supporting levers, with implementation and guardrails (Q3, Q4) | 1.0–1.25 |
| Projected impact assessment | Scenario outcomes, sensitivity, what it costs in volume | 0.75–1.0 |
| Appendix (light) | Data design note, method summary, key assumptions — not counted in body | as needed |

Deliverable: CRO-addressed report, recommendation-led, every claim sourced to the controlled workbook.

## Workstream K — Deck Development

Owner: Engagement Manager    Decision it informs: A stakeholder deck that complements the report and carries the story.

Format is at the team's discretion; below is a recommended 14-slide spine. For each slide: purpose, key message, charts, and the takeaway the audience should leave with.

| # | Slide / purpose | Key message | Charts | Takeaway |
| --- | --- | --- | --- | --- |
| 1 | Title | Engagement & ask | — | Who, what, for whom |
| 2 | Executive summary | One recommendation, one number | Impact callout | We know the answer |
| 3 | Context & problem | Growth strained portfolio quality | Market/portfolio snapshot | Why this matters now |
| 4 | Approach | Data → segments → EWS → policy | Framework diagram | Method is rigorous |
| 5 | Portfolio diagnostic | Where risk concentrates today | Delinquency + vintage | Current-state pain |
| 6 | Risk segmentation | Segments differ materially | Segment risk bars | Q1 answered |
| 7 | Risk × value matrix | Grow some, contain others | 2×2 bubble matrix | Where value lives |
| 8 | Channels & unit economics | Cheap acquisition isn’t cheap | CAC vs CLV / default | Q2 answered |
| 9 | Product / ticket / tenure | Best growth-vs-risk cells | Heatmap | Q3 answered |
| 10 | Early-warning system | We see stress early | EWS funnel + lead time | Proactive, not reactive |
| 11 | Recommendations | Headline + supporting levers | Policy lever table | Q4 answered |
| 12 | Impact assessment | What it delivers & costs | Scenario + tornado | Quantified upside |
| 13 | Executive dashboard | What leadership monitors | Dashboard mock-up | Q5 answered |
| 14 | Roadmap & next steps | How to implement | Phased timeline | Make it real |

Deliverable: 12–14 slide deck, visual system consistent with the report, one message per slide.

# 3. Dependency Map

Workstreams chained in execution order. “CP” marks critical-path items — any slip here consumes buffer directly. Dashboards (H) run in parallel off EDA outputs and are not on the critical path.

| WS | Workstream | Depends on | Enables | Critical path? |
| --- | --- | --- | --- | --- |
| A | Problem framing | — | B, I, J, K | CP |
| B | Synthetic data design | A | C | CP |
| C | Data generation | B | D, E, F | CP |
| D | Exploratory analysis | C | E, G, H | CP |
| E | Segmentation | C, D | F, G, I | CP |
| F | Early-warning system | C, E | G, I | CP |
| G | Portfolio optimization | D, E, F | I | CP |
| H | Executive dashboards | D (+E, F, G) | J, K | Parallel |
| I | Recommendation dev. | E, F, G | J, K | CP |
| J | Report development | A, I (+H) | QA / submit | CP |
| K | Deck development | A, I, J (+H) | QA / submit | CP |

Critical path (longest dependent chain): A → B → C → D → E → F → G → I → J → K → QA → Submit. Segmentation (E) and the early-warning system (F) are the highest-leverage nodes: they feed both optimisation and the recommendation, so their quality gates (Gates 3 and 4) get the most senior review time.

# 4. Day-by-Day Timeline Until June 10

Ten calendar days, engineered to reach “submission-ready” by end of Day 9 so that June 10 is a protected buffer and final-review day. Each day lists objectives, tasks, the gate/checkpoint that closes it, and the expected output. Critical-path tasks are flagged [CP].

## Day 1 · Mon June 1 — Framing & data design [CP]

Objective: Lock the problem, success metrics and the complete data schema before a single row is generated.

Tasks

- Kickoff: confirm objective, scope, definitions of default/delinquency, success metrics (WS A). [CP]

- Draft engagement charter and storyline hypothesis (“we expect to recommend …”).

- Design four-table schema, variable dictionary (must/nice-to-have), and target distributions (WS B). [CP]

- Set up repo, controlled workbook shell, version control and naming conventions (PMO).

Checkpoint / gate: End-of-day review of charter + schema against the brief's data table and five key questions.

Expected output: Signed charter; complete data dictionary; documented design targets and assumptions log.

## Day 2 · Tue June 2 — Data generation → Gate 1 [CP]

Objective: Generate a behaviourally coherent dataset and pass the data-realism gate.

Tasks

- Build seeded, parameterised generator; latent-risk-driven correlations (WS C). [CP]

- Produce customers, loans, repayments, behaviour tables at target volumes. [CP]

- Run data-quality + realism + distribution checks against design targets.

- Fix any relationship that contradicts the brief's expected directions; re-generate.

Checkpoint / gate: GATE 1 — Synthetic data review (acceptance criteria in §6).

Expected output: Four validated tables + data dictionary + Gate 1 sign-off log.

## Day 3 · Wed June 3 — EDA & diagnostics → Gate 2 [CP]

Objective: Diagnose the current-state portfolio and pre-stage the deck's diagnostic exhibits.

Tasks

- Portfolio diagnostics, cohort/vintage, delinquency & roll-rate analysis (WS D). [CP]

- Channel performance and unit-economics (CAC, CLV proxy, payback) by segment.

- Curate 10–15 exhibit chart pack; write the one-line insight under each.

- Spin up dashboard skeleton in parallel off EDA outputs (WS H, parallel).

Checkpoint / gate: GATE 2 — EDA review: insights are decision-relevant, not descriptive.

Expected output: EDA notebook + chart pack with insights; dashboard skeleton; Gate 2 sign-off.

## Day 4 · Thu June 4 — Segmentation → Gate 3 [CP]

Objective: Produce interpretable, materially separated, stable risk/value segments (Q1).

Tasks

- Run heuristic, tree-based and clustering methods; compare on the selection criteria (WS E). [CP]

- Build risk × value matrix and product–ticket–tenure cells.

- Stability test on bootstrap samples; “name each segment in one line” test.

- Define the policy hook for each segment (feeds G and I).

Checkpoint / gate: GATE 3 — Segmentation review: separated, interpretable, actionable, stable.

Expected output: 4–6 named segments with profiles, sizes, risk/value metrics; Gate 3 sign-off.

## Day 5 · Fri June 5 — Early-warning system [CP]

Objective: Engineer behavioural features and build a governable delinquency-prediction flag (Q5 enabler).

Tasks

- Feature engineering: trends/deltas, streaks, volatility spikes (WS F). [CP]

- Fit scorecard/logistic + GBM (monotonic) on forward 60–90-day default target. [CP]

- Design trigger rules and green/amber/red thresholds tied to collections capacity.

- Extend dashboards with segment and EWS views (WS H, parallel).

Checkpoint / gate: End-of-day model readout: AUC/KS, lift, and — critically — expected lead time.

Expected output: EWS scorecard + trigger rules + draft threshold table.

## Day 6 · Sat June 6 — EWS validation + optimisation → Gate 4 [CP]

Objective: Validate the model out-of-time and begin portfolio optimisation.

Tasks

- Train/test + out-of-time validation; stability and sensitivity checks (backtesting). [CP]

- Finalise thresholds against false-positive vs. missed-default cost.

- Begin pricing/tenure/approval optimisation by segment (WS G). [CP]

- Set up baseline vs. scenario framework with shared assumptions.

Checkpoint / gate: GATE 4 — Model review: validated, stable, governable, lead time meaningful.

Expected output: Validated EWS pack; optimisation scenario framework live; Gate 4 sign-off.

## Day 7 · Sun June 7 — Optimisation & recommendations → Gate 5 [CP]

Objective: Complete scenario/sensitivity analysis and convert findings into prioritised, costed policy.

Tasks

- Run baseline + 2–3 policy scenarios; project default, volume, revenue, risk-adj. contribution (WS G). [CP]

- Sensitivity / tornado on key assumptions incl. macro stress; explicit growth-vs-risk trade-off.

- Prioritise policies (impact × feasibility × speed); pick headline + 2–3 levers (WS I). [CP]

- Build impact table with assumption set and plausible ranges.

Checkpoint / gate: GATE 5 — Recommendation review: feasible, prioritised, quantified, guardrailed.

Expected output: Scenario comparison + sensitivity; prioritised recommendation set with impact table; Gate 5 sign-off.

## Day 8 · Mon June 8 — Dashboards + report draft [CP]

Objective: Finalise dashboards and produce a complete first draft of the CRO report.

Tasks

- Finalise four dashboard views from the controlled source (WS H).

- Write full report draft: exec summary → segmentation → EWS → policy → impact (WS J). [CP]

- Reconcile every report number to the controlled workbook (one number, one source).

- Draft appendix: data design, method, assumptions.

Checkpoint / gate: End-of-day read-through of full report draft against the page-allocation plan.

Expected output: Dashboard mock-ups final; complete report draft (4–6 pp.) reconciled to source.

## Day 9 · Tue June 9 — Deck build + dedicated validation → Gate 6 [CP]

Objective: Build the deck, run the full validation phase, and reach submission-ready.

Tasks

- Build 12–14 slide deck on the recommended spine; one message per slide (WS K). [CP]

- Run the full backtesting & validation plan (§7): model, segmentation, recommendation, dashboard. [CP]

- Storyline test: report and deck tell the same story and lead with the recommendation.

- Visual consistency pass across report, deck and dashboards.

Checkpoint / gate: GATE 6 — Deck review + validation sign-off; declare “submission-ready”.

Expected output: Final deck; completed validation log; consistent visual system; Gate 6 sign-off.

## Day 10 · Wed June 10 — Buffer, final QA & submit → Gate 7

Objective: Protected buffer: final partner-grade QA and submission — no new content.

Tasks

- Run the final submission checklist (§8) end-to-end (PMO + EM).

- Partner-style cold read: would a CRO act on this? Is every number defensible?

- Fix only critical defects; absorb any residual slip from earlier days.

- Package, name, and submit both components with buffer before deadline.

Checkpoint / gate: GATE 7 — Final submission review and partner sign-off.

Expected output: Submitted Credit Policy Recommendation Report + deck; signed checklist; Gate 7 log.

Buffer & contingency note. If any critical-path gate fails, the team de-scopes nice-to-have variables and the third optimisation scenario first (never the validation phase), and pulls work forward into the Day 10 buffer only as a last resort. The validation phase (Day 9) and final QA (Day 10) are non-negotiable and protected against compression.

# 5. Risk Register

Probability (P) and Severity (S) rated Low / Med / High. Score = exposure if unmanaged. Every risk has a named owner, an early indicator to watch, and a mitigation. Contingencies are the move if mitigation fails.

| Risk | P | S | Mitigation | Contingency / owner |
| --- | --- | --- | --- | --- |
| Unrealistic synthetic data undermines every downstream result | Med | High | Causal-by-construction generator; hard realism gate (Gate 1); directions validated vs. brief | Re-parameterise generator; reduce scope to must-have vars · Data Lead |
| Weak / unstable segmentation that a risk committee won’t trust | Med | High | Test 3 methods; enforce separation + interpretability + stability criteria (Gate 3) | Fall back to transparent grade/behaviour rule-based segments · Risk Consultant |
| Recommendations not operationally feasible or not costed | Med | High | Feasibility + financial-plausibility checks; guardrails; impact ranges not point estimates | Down-scope to one headline policy with conservative impact · EM |
| EWS overfitting / inflated accuracy | Med | High | Out-of-time validation; monotonic constraints; prefer scorecard; report lift + lead time | Ship rule-based triggers only; drop fragile model · Data Lead |
| Weak impact estimation the panel can’t defend | Med | Med | One-number-one-source workbook; explicit assumptions; sensitivity analysis | State ranges + label as directional; show method · EM |
| Deck–report–story disconnect | Med | Med | Shared storyline locked Day 1; Gate 6 storyline test; same source for all numbers | Rebuild deck from report's executive summary spine · EM |
| Time overrun on the critical path | Med | High | Daily stand-ups; gates block downstream start; Day 10 protected buffer | De-scope nice-to-haves and 3rd scenario; never the validation phase · PMO |
| Single point of failure (one person, one machine) | Low | High | Version control; controlled workbook; documented seeds for reproducibility | Re-run from seeds; pair on critical-path tasks · PMO |
| Scope creep / gold-plating the data instead of the answer | Med | Med | Recommendation-first principle; must/nice-to-have discipline; gate acceptance criteria | EM cuts scope to the five key questions · EM |

# 6. Quality Gates

Seven mandatory checkpoints. A gate is binary: pass, or fix-then-pass. PMO logs each before the dependent workstream begins. For each gate: acceptance criteria, common failure modes, and required fixes.

## Gate 1 — Synthetic data review

When: End of Day 2    Owner: Data Science Lead

Acceptance criteria

- Must-have fields complete; keys unique and joinable; values within allowed ranges

- Panel completeness: every active loan has a row per period until closure/charge-off

- All brief-specified relationships hold directionally (weaker profile/volatility/cheap channel → higher risk)

- Blended default and product/grade/channel mixes within design-target tolerance

Common failure modes

- Correlations bolted on after generation, producing inconsistent joins

- Implausible marginals (negative tenure, absurd APR, zero-variance behaviour)

- Default rate far from realistic emerging-market range

Required fixes

- Re-seed and re-generate from latent-risk model; re-run distribution validation; document assumptions

## Gate 2 — EDA review

When: End of Day 3    Owner: EM + Senior Risk Consultant

Acceptance criteria

- Each exhibit answers or advances a key question, not just describes the data

- Cohort/vintage, roll-rate, channel and unit-economics analyses all present

- A one-line decision-relevant insight sits under every chart

Common failure modes

- Descriptive dashboards with no “so what”

- Unit economics missing (revenue not netted against expected loss, CAC, servicing)

- Channel analysis that ignores CAC payback / CLV

Required fixes

- Re-frame each exhibit around the decision; add the missing economics; cut charts that carry no insight

## Gate 3 — Segmentation review

When: End of Day 4    Owner: Senior Risk Consultant

Acceptance criteria

- Segments materially separated on risk and value

- Each nameable in one business line and tied to a policy hook

- Stable across bootstrap resamples and cohorts

Common failure modes

- Statistically tidy but business-meaningless clusters

- Too many segments to action; unstable membership

- Segments with no differentiated policy implication

Required fixes

- Reduce to 4–6 actionable segments; switch to interpretable method if clusters fail the business test; re-test stability

## Gate 4 — Model review

When: End of Day 6    Owner: Data Science Lead + Risk Consultant

Acceptance criteria

- Validated out-of-time; AUC/KS and lift reported honestly

- Stable across samples; sensible feature behaviour (monotonic where expected)

- Meaningful average lead time before 90+ default; thresholds tied to capacity

Common failure modes

- Overfit (great in-sample, weak out-of-time); leakage from future periods

- Black-box model a risk committee can’t govern

- Thresholds set without regard to false-positive cost or collections capacity

Required fixes

- Remove leaking features; simplify to scorecard; re-validate out-of-time; recalibrate thresholds on cost trade-off

## Gate 5 — Recommendation review

When: End of Day 7    Owner: Engagement Manager

Acceptance criteria

- Headline + 2–3 supporting levers, each specific (who/what/segment/magnitude)

- Each quantified (Δ default, Δ volume, Δ revenue, net risk-adj. contribution) with assumptions and ranges

- Operationally feasible and guardrailed

Common failure modes

- Generic advice (“tighten underwriting”) with no magnitude

- Impact asserted without method or sensitivity

- Policy that ignores volume cost or implementation reality

Required fixes

- Make each lever specific and costed; add sensitivity; add a guardrail metric per policy

## Gate 6 — Deck review

When: End of Day 9    Owner: EM + PMO

Acceptance criteria

- One message per slide; deck and report tell the same story; recommendation-led

- Every number reconciles to the controlled workbook

- Consistent visual system across report, deck and dashboards

Common failure modes

- Data-dump slides; story buried; inconsistent figures between artefacts

- Charts without takeaways; cluttered, off-brand visuals

Required fixes

- Cut to one message per slide; reconcile all numbers to source; apply single visual system; add takeaway lines

## Gate 7 — Final submission review

When: Day 10    Owner: Engagement Manager (partner sign-off)

Acceptance criteria

- Final submission checklist (§8) fully green

- Cold read passes the “would a CRO act on this?” test

- Both components packaged, named correctly, and submitted with buffer before the deadline

Common failure modes

- Last-minute content changes introducing new errors

- Mismatched file names/versions; missing appendix or references

- Submitting at the wire with no buffer

Required fixes

- Freeze content; fix only critical defects; verify package; submit early

# 7. Backtesting & Validation Plan

A dedicated validation phase (Day 9, protected) tests the four pillars before submission. Exact checks below.

## 7.1 Model validation (Early-Warning System)

- Train–test validation. Split by time, not at random: train on earlier cohorts, test on later ones; report AUC, KS, precision/recall and decile lift on the held-out period.

- Stability testing. Re-fit on bootstrap samples; check coefficient/feature-importance stability and Population Stability Index (PSI) between development and recent windows.

- Sensitivity testing. Vary the alert threshold and the forward window; confirm precision and lead time degrade gracefully, not catastrophically; check no single feature dominates implausibly.

- Leakage check. Confirm no feature encodes the outcome (e.g., post-default behaviour) and that all features are knowable at prediction time.

## 7.2 Segmentation validation

- Business interpretability. Each segment described in one line a risk committee accepts; profiles align with intuition and the brief's expected relationships.

- Statistical robustness. Separation statistics (e.g., silhouette / between-vs-within variance); membership stability on resampling; default/value differences across segments are material and significant.

## 7.3 Recommendation validation

- Real-world feasibility. Each policy implementable with existing levers (pricing grid, cut-off, tenure caps, channel allocation); name the owner and the system change.

- Financial plausibility. Impact recomputed from the controlled workbook; sanity-check against base rates; confirm the growth-vs-risk trade-off is shown and the numbers reconcile to the dashboard.

## 7.4 Dashboard validation

- Executive usability. CRO view answers “are we within appetite this week?” in one screen; RAG status unambiguous; no analyst jargon.

- Decision usefulness. Each KPI maps to an action and a threshold; figures tie out to the report; the four views answer Q5 collectively.

# 8. Final Submission Checklist

Partner sign-off checklist. Every line must be green before submission. Tick column intentionally blank for the team to mark.

## 8.1 Analytics

| ✓ | Item |
| --- | --- |
| ☐ | All five key questions explicitly answered and findable in the report and deck |
| ☐ | EDA insights are decision-relevant; unit economics include expected loss, CAC and servicing |
| ☐ | Cohort/vintage, delinquency, roll-rate and channel analyses present |

## 8.2 Data & models

| ✓ | Item |
| --- | --- |
| ☐ | Synthetic data passed Gate 1; data dictionary and assumptions log attached |
| ☐ | Generator is seeded and reproducible; results regenerate from seeds |
| ☐ | EWS validated out-of-time; AUC/KS, lift and lead time reported honestly; no leakage |
| ☐ | Segmentation separated, interpretable, stable; method choice justified |

## 8.3 Assumptions

| ✓ | Item |
| --- | --- |
| ☐ | All material assumptions listed in one place with rationale |
| ☐ | Macro / sensitivity ranges stated; impact shown as ranges, not false-precision point estimates |

## 8.4 Recommendations

| ✓ | Item |
| --- | --- |
| ☐ | One headline policy + 2–3 supporting levers, each specific and costed |
| ☐ | Each policy feasible, has an owner, a guardrail metric, and an implementation note |
| ☐ | Growth-vs-risk trade-off explicit; what each policy costs in volume is stated |

## 8.5 Report

| ✓ | Item |
| --- | --- |
| ☐ | 4–6 pages, addressed to the CRO, recommendation-led |
| ☐ | Contains exec summary, segmentation findings, EWS logic, policy recommendation, impact assessment |
| ☐ | Every number reconciles to the controlled workbook (one number, one source) |

## 8.6 Deck

| ✓ | Item |
| --- | --- |
| ☐ | 12–14 slides, one message per slide, leads with the recommendation |
| ☐ | Every chart has a takeaway line; figures match the report exactly |

## 8.7 Visual consistency & storyline

| ✓ | Item |
| --- | --- |
| ☐ | Single visual system (fonts, colours, chart styles) across report, deck and dashboards |
| ☐ | Report and deck tell the same story; storyline test passed at Gate 6 |

## 8.8 References, appendix & QA

| ✓ | Item |
| --- | --- |
| ☐ | Appendix: data design note, method summary, key assumptions |
| ☐ | Sources/citations for any external benchmarks; nothing unattributed |
| ☐ | Final partner-style cold read passed: a CRO could act on this and defend every number |
| ☐ | Files named per convention, packaged, and submitted with buffer before June 10 deadline |

End of execution roadmap. This plan is engineered so that quality is built in at each gate rather than inspected at the end, and so that the team reaches submission-ready a full day before the deadline.